## Slide 1
ROYAL COMPASS TRAVELS
Month 1 Digital
Marketing Plan
Website search · Instagram · Meta Ads · Lead system
royalcompasstravels.com
Notes: Introduce the plan as a first-month foundation and testing plan. Keep it short: we'll walk through what we'll do, how we'll measure it, and what it costs.

## Slide 2
OBJECTIVE
What Month 1 is for
Build stronger online visibility and establish an initial lead-generation system.
Visibility
A clearer, better-structured website and a consistent Instagram presence.
Enquiries
A tested ad setup and a simple system that sends every website enquiry to your team.
Royal Compass Travels · Month 1 Plan
2
Notes: The first month is about foundations and learning, not scale. Two outcomes: visibility (website + Instagram) and an enquiry system (ads + lead area).

## Slide 3
WEBSITE SEARCH OPTIMIZATION
Helping customers find and understand you
SEO
Search engines
Page titles & descriptions
Clear headings and structure
Relevant travel keywords
Google Search Console setup
GEO
AI-based search tools
Clear business information
Services & destinations explained
Consistent details across pages
Structured, easy-to-read content
AEO
Customer questions
Common traveller questions
Short, direct answers
Helpful FAQ sections
Better informational pages
Royal Compass Travels · Month 1 Plan
3
Notes: SEO: making the site readable and relevant for Google. GEO: making information clear for AI-based search tools like ChatGPT or Google's AI answers. AEO: answering real customer questions directly. They overlap — the same clean pages help all three. Search visibility builds over time; Month 1 sets the foundation.

## Slide 4
INSTAGRAM
A consistent, travel-focused presence
1
post every day
30
posts per month
10
reels per month
Content themes
Destination inspiration
Travel tips
Travel information
Our services
Packages & offers
FAQs
Trust-building
How it supports the plan
Builds trust when people check your profile after seeing an ad
Shows which topics your audience responds to
Gives us material to reuse in ads
Royal Compass Travels · Month 1 Plan
4
Notes: 30 posts plus 10 reels in the month, all travel-focused. Content plan shared in advance for approval. Real trip photos and videos from your side make the content more credible. Growth on Instagram is gradual; we'll track which content people save, share and message about.

## Slide 5
META ADS
A focused test on Facebook & Instagram
5
creatives developed
Different images, messages and angles
›
Test
all five
Early spend spread evenly to compare
›
Best 3
keep running
Weaker ads paused based on results
›
Optimise
through the month
Audience and budget refined
₹10,000
ad budget, paid by you directly to Meta
Focus on relevant enquiries
We judge ads by the quality and cost of enquiries — not likes or cheap clicks. Month 1 is a testing budget to learn what works for your audience before any decision to spend more.
Royal Compass Travels · Month 1 Plan
5
Notes: Five creatives are made and tested; the best three continue and are optimised. The ₹10,000 is spent from your own ad account, so you can see every rupee. We need from you: Meta Business access, priority destinations/packages, any offers, and quick approval of creatives. We don't predict a lead count before the test — the test tells us the real cost per enquiry.

## Slide 6
WEBSITE & LEAD SYSTEM
Every website enquiry, straight to your team
Visitor
Finds you via search,
Instagram or ads
Enquiry form
Name, phone,
destination, dates
Your admin area
Protected; only you
hold the password
Your team
Calls, WhatsApp,
quotes & bookings
Legal pages
Privacy, terms, cancellation & refund
Search Console
Connected & verified with Google
Website fixes
Issues affecting experience or enquiries
Client-controlled
You own the admin login and leads
Royal Compass Travels · Month 1 Plan
6
Notes: Enquiries go to your own protected admin area — not to us. You set and keep the password. Your team handles follow-up, quotations and bookings; quick replies make a real difference. Legal pages are drafted from your actual policies for your review. This is fixes and setup, not a website redesign.

## Slide 7
MONTH 1 EXECUTION
Four weeks, step by step
WEEK 1
Set up
Website audit
Access & setup
Search Console
Content & ad planning
WEEK 2
Build
SEO improvements
Website fixes & legal pages
Admin lead area
Ad creatives
WEEK 3
Launch
Meta Ads test goes live
Instagram continues
Monitor early results
Adjust
WEEK 4
Review
Run best-performing ads
Content continues
Review the numbers
Month-end report
To keep this on schedule, we'll need from you: account access, package and destination details, photos/videos, and timely approvals.
Royal Compass Travels · Month 1 Plan
7
Notes: Instagram posting starts as soon as the content plan is approved. Week 1 depends on receiving access; any delay shifts the later steps. Ads may need a day or so for Meta's review. If the ad budget isn't fully used by day 30, the test can run a few extra days to finish it.

## Slide 8
WHAT WE WILL MEASURE
Clear numbers, reported at month-end
Website
Search impressions
Clicks from Google
Search queries
Top-performing pages
Instagram
Reach
Engagement
Profile visits
Content performance
Meta Ads
Spend
Impressions & reach
CTR & CPC
Leads & cost per lead
What matters most: relevant enquiries and what each one costs. Reach and impressions are shown for context.
Royal Compass Travels · Month 1 Plan
8
Notes: A short mid-month update and a month-end report: work completed, real numbers from Google Search Console, Instagram and Meta, what worked, what didn't, and our recommendation. Please share feedback on lead quality — it's what lets us improve targeting.

## Slide 9
INVESTMENT
Month 1
OUR SERVICE FEE
₹20,000
SEO, GEO & AEO · Instagram · Ad creatives & management · Website fixes & lead system · Reporting
META ADS BUDGET
₹10,000
Paid by you directly to Meta from your own ad account. Not included in our fee.
+
TOTAL INITIAL OUTLAY
₹30,000
₹20,000 to us + ₹10,000 to Meta
Please note: the ₹10,000 ad spend is not included in the ₹20,000 service fee. Meta may apply taxes on ad spend as per its billing terms.
Royal Compass Travels · Month 1 Plan
9
Notes: The ad budget never passes through us — you add your own payment method in Meta Ads Manager and can see all spend there. Payment terms for the service fee will be confirmed in writing.

## Slide 10
MONTH 1 GOAL
A solid foundation,
and real data to decide the next step
01
Set up
the foundation
02
Test
audience & creatives
03
Generate
initial enquiries
04
Decide
whether continuing or scaling makes sense
Digital marketing results depend on audience, offer, creative, competition, budget and customer response. Specific rankings, traffic, leads or sales are not guaranteed.
Notes: Close with the goal: foundation, test, initial enquiries, then a data-based decision together. Invite questions. After the call, send a written summary and the access/information checklist within 24 hours.